## MOD 4
PO / Instructions | Material | Metcut Job | Split | Phase | Qtty Done and Running | Qtty planned | Status | DyT | Comment | Contact
DPL 2017-2234 | Inco 718 | 13355 | 0 | Reception Matière | 51 | 51 | Receipt 06/12/17 |  | 3 staircases | J rouches
DPL 2017-2234 | Inco 718 | 13355 | 1 | Load Control | 2 | 16 | In Progress |  |  | A Gotzfried
DPL 2017-2234 | Inco 718 | 13355 | 2 | Load Control | 1 | 16 | In Progress |  |  | S Blas
DPL 2017-2234 | Inco 718 | 13355 | 3 | Load Control | 0 | 16 | Attente Dispo Lab
DPL 2017-1986 | Inco 718 | 13354 | 0 | Reception Matière | 18 | 18 | Receipt 01/12/17 |  | Creep avec rampe simple sur split 1, creep avec ecrouissage sur split 2 Données brutes envoyées séparemment. | J rouches
DPL 2017-1986 | Inco 718 | 13354 | 1 | Creep | 8 | 14 | In Progress |  |  | J Papasidero
DPL 2017-1986 | Inco 718 | 13354 | 2 | Creep | 3 | 4 | In Progress
DPL 2017-1786 | Inco 718 | 13350 | 0 | Reception Matière | 3 | 3 | Receipt 20/11/17 |  |  | J rouches
DPL 2017-1786 | Inco 718 | 13350 | 1 | Fatigue Incrementale | 1 | 1 | In Progress | 2017-01-05 |  | J Papasidero
DPL 2017-1786 | Inco 718 | 13350 | 2 | Relaxation Incrementale | 1 | 1 | In Progress | 2017-01-05
DPL 2017-1786 | Inco 718 | 13350 | 0 | Creep Incrementale | 1 | 1 | Emission rapport | 2017-01-05
DPL 2017-1985 | DMD 0776 - 6.4 | 13346 | 0 | Reception Matière | 10 | 10 | Receipt 01/12/17 | 2017-11-15 | Le stepcase étant long (5 niveaux) nous estimons un nouveau délai au 03/01/18 | J rouches
DPL 2017-1985 | DMD 0776 - 6.4 | 13346 | 1 | Strain Control | 0 | 6 | In Progress | 2017-01-03 |  | H Sistach
DPL 2017-1985 | DMD 0776 - 6.4 | 13346 | 2 | Load Control | 0 | 4 | In Progress | 2017-01-03 |  | S Rix
DPL 2017-1840 | MIM Inco 718 | 13338 | 0 | Reception Matière | 10 | 10 | Receipt 20/11/17 | 2017-11-10 |  | J rouches
DPL 2017-1840 | MIM Inco 718 | 13338 | 1 | Load Control | 10 | 10 | Completed 15/11/17 | 2017-12-11 |  | H Sistach
T Grall
DPL 2016-1522 | DMD 0456 - Inco 718 p.q. | 13324 | 0 | Reception Matière | 23 | 23 | Receipt 20/11/17 | 2017-11-10 |  | J rouches
DPL 2016-1522 | DMD 0456 - Inco 718 p.q. | 13324 | 1 | Load Control | 23 | 23 | Completed 15/11/17 | 2017-12-21 |  | E Fessler
DPL 2017-1551 | TA6V PQ | 13320 | 0 | Reception Matière | 74 | 74 | Receipt 01/09/17 | 2017-11-10 | Fractos prévues fin de semaine prochaine | J rouches
DPL 2017-1551 | TA6V PQ | 13320 | 1 | Load Control | 26 | 26 | Completed 27/10/17 | 2017-11-10 |  | PJ Renaud
DPL 2017-1551 | TA6V PQ | 13320 | 2 | Load Control | 48 | 48 | Completed 03/11/17 | 2017-11-10
DPL 2017-1551 | TA6V PQ | 13320 | 3 | Fractography | 0 | 74 | In Progress | 2017-11-24
DPL 2017-1551 | TA6V PQ | 8003 | 13320 | 1 | 91 Completed - Fracto En cours | 26 | 26 | 2017-11-24 | format 525 : Fatigue + FRACTO chez Metcut US (délai incluant fractos) 26 ep chez Metcut US pour fracto. Fractos prévues fin de semaine prochaine | PJ Renaud
DPL 2017-1551 | TA6VPQ | 8003 | 13320 | 2 | 91 Completed - Fracto En cours | 48 | 48 | 2017-11-24 | format 941 : Fatigue + FRACTO chez Metcut US (délai incluant fractos) 47 ep rompues chez Metcut US pour fracto Fractos prévues fin de semaine prochaine | PJ Renaud
DPL 2017-1042 | Inco 718 | 8003 | 13290 | 0 | 90 Emission Rapport | 3 | 3 | 2018-01-01 | Merci de nous faire savoir à chaque fois que les fichiers crete à crete vous sont nécessaires. Eprouvette DV10-11 expédiée le 17/11 et éprouvette DV10-9 expédiée le 30.11.2017 DV10-12 expédiée le 14.12.2017 | J Papasidero

## MOD 3 (2)
PO / Instructions | Metcut Job | Split | Phase | Qtty Done and Running | Qtty planned | Status | DyT | Comment
DPL 2017-2234 | 8003-13285 | 0 | Reception Matière | 20 | 20 | Completed 10/12/17 | 2017-12-12 | reception le 10/12
|  | A | Machining | 20 | 20 | Completed
Contact |  | B | ShP | 20 | 20 | Completed
JRouches / L Menut-Tournadre/S Blas |  | 1 | Fatigue Strain Control | 3 | 10 | In progress | 2017-12-12
|  | 2 | Fatigue Load Control | 7 | 10 | Standby | 2017-12-18

## MOD 3
PO / Instructions | Metcut Job | Split | Phase | Qtty Done and Running | Qtty planned | Status | DyT | Comment
DPL 2017-1568 | 8003-13285 | 0 | Reception Matière | 20 | 20 | Completed 10/12/17 | 2017-12-12 | reception le 10/12
|  | A | Machining | 20 | 20 | Completed
Contact |  | B | ShP | 20 | 20 | Completed
JRouches / L Menut-Tournadre/S Blas |  | 1 | Fatigue Strain Control | 3 | 10 | In progress | 2017-12-12
|  | 2 | Fatigue Load Control | 7 | 10 | Standby | 2017-12-18

## MOD 2
PO | Contact | Comment | Metcut Job: 8003-13285 | Reception Matière | A- Machining | B- ShP | 1- Strain Control | 2- Load Control
DPL 2017-1568 | J rouches |  | Qtty planned | 20 | 20 | 20 | 3 | 7
| L Tournadre |  | Qtty Done and Running | 20 | 20 | 20 | 10 | 10
| S Blas |  | Status | Completed | Completed | Completed | In progress | Standby
|  |  | DyT | 2017-12-12 |  |  | 2017-12-12 | 2017-12-18
PO | Contact |  | Metcut Job: 8003-13285 | Reception Matière | A- Machining | B- ShP | Comment
DPL 2017-1568 | J rouches |  | Qtty planned | 20 | 20 | 20
| L Tournadre |  | Qtty Done and Running | 20 | 20 | 20
| S Blas |  | Status | Completed | Completed | Completed
|  |  | DyT | 2017-12-12

## MOD 1
Safran Aircraft Engines
PO | Instructions |  |  | Reception matière |  | Contact
DPL 2017-1568 |  |  |  | Date Prévue | 2017-12-12 | JRouches / L Menut-Tournadre/S Blas
Metcut Job |  |  |  | Qtty | 24
8003-13285 |  |  |  | Date Reception | 2017-12-10
Split | Phase | Qtty | Qtty | Status | DyT | Comment
A | Machining | 20 | 20 | Completed |  | données brutes cdczkn,ckze,clzek,
B | ShP | 20 | 20 | Completed
1 | Fatigue Strain Control | 3 | 10 | In progress | 2017-12-12
2 | Fatigue Load Control | 7 | 10 | Standby | 2017-12-18
PO | Instructions |  |  | Reception matière |  | Contact
DPL 2017-1568 |  |  |  | Date Prévue | 2017-12-12 | JRouches / L Menut-Tournadre/S Blas
Metcut Job |  |  |  | Qtty | 24
8003-13285 |  |  |  | Date Reception | 2017-12-10
Split | Phase | Qtty | Qtty | Status | DyT | Comment
A | Machining | 20 | 20 | Completed |  | données brutes cdczkn,ckze,clzek,
B | ShP | 20 | 20 | Completed
1 | Fatigue Strain Control | 3 | 10 | In progress | 2017-12-12
2 | Fatigue Load Control | 7 | 10 | Standby | 2017-12-18